## CPC '24-'25 Budget WCC Bio
1 | Funding Source | 1st April 2024 - 2025 Budget Items | Firm Quote or Estimate | Frequency in CPC Financial Year or Number | Units | Approx Month/s for doing the work | Budget Estimate per Item Excl VAT | TOTAL Budget for the Financial Year | Bio-A/C Approx. £14,895 at 1st Apr '24 See Note 1. | Notes
2 | NOTE 1: At April 2024, the Biodiversity A/C will stand at approx. £14,895.27. (£14,366.05 as reported by Ken at the PC Meeting 18 Sept '23, minus £1,620.00 incl VAT paid to Xtreme Tree Care to remove fallen dead trees from Pond 1, beside Dinglebury, during Sep 2023, plus £2,149.22 from WCC on or around 10 April '23.) | [7 empty] | 12338.95 | SUB-TOTAL
3 | Biodiversity A/C | IN ACCORDANCE WITH THE BIODIVERSITY OFFSET MANAGEMENT PLAN:
4 | Biodiversity A/C | Neutral Grassland:
5 | Biodiversity A/C | OBJECTIVE: Enhance the areas of neutral grassland to increase species diversity and undertake the long-term annual management of neutral grassland. | [8 empty] | 14895.27
6 | Biodiversity A/C | HOW: Spray creeping thistle & docks on the Mound by spot spraying in spring and autumn. | Estimate | 2 | Days | Apr & Sep | 525 | 1050 |  | In his budget David Cole allowed £415 for 2019 & 2020, not started. Money not spent £830.
7 | Biodiversity A/C | HOW: Spread green hay, seeds or plugs. | Estimate | 1 | Visit | Sep | 1600 | 1600 |  | In his budget David Cole allowed £1,600 for green hay in 2022, not started. Money not spent £1,600
8 | Biodiversity A/C | OR buy perennial Native Wildflower seeds from the £1,600. 50x25m=>6kg=> £786 approx. |  |  |  | Sep |  | 0 |  | https://thegrasspeople.com
9 | Biodiversity A/C | OR buy perennial Native Wildflower plugs from the £1,600. 12 plugs=£28.00 = 348 plugs for £814 approx. |  |  |  | Sep |  | 0 |  | https://www.wildflowershop.uk/shop/Vipers-Bugloss-Plugs-p222839417
10 | Biodiversity A/C | Net fencing to protect wildflower seeds / plugs from rabbits etc. | B&Q | 4 | Item | Sep | 42 | 168 |  | B&Q Easipet PVC Coated Green Chicken/Rabbit Wire Mesh for Aviary Fencing Garden 50mm x 120cm x 50m = £42.00.
11 | Biodiversity A/C | Timber posts for net fencing, to protect wildflower seeds / plugs from rabbits etc. | B&Q | 40 | Item | Sep | 9 | 360 |  | B&Q Klikstrom Square Wooden Fence post (H)1.8m (W)45mm
12 | Biodiversity A/C | Mechanical cutting of blackthorn in the west side of the Mound, to improve views if the Malvern Hills. Outside bird nesting season. | Meadowcare Quote QU-0038, 2 Feb '23 | 3 | Days | Sept to Jan | 475 | 1425
13 | Operating A/C | Long Term Annual Management of Neutral Grassland:
14 | Operating A/C | HOW: Cut Grass. Manage by first cutting in mid summer with removal of cuttings (to compost areas on site) with occasional light scarification to remove any thatch and create base patches to aid the spread of wildflower species in the grassland areas. | Meadowcare Quote QU-0038, 2 Feb '23 | [6 empty] | In his budget David Cole allowed £1,000 per year.
15 | Operating A/C | HOW: Cut Grass. Manage by second cutting in late summer with removal of cuttings (to compost areas on site) with occasional light scarification to remove any thatch and create base patches to aid the spread of wildflower species in the grassland areas. | Meadowcare Quote QU-0038, 2 Feb '23
16 | Biodiversity A/C | Acid Grassland:
17 | Biodiversity A/C | OBJECTIVE: Extend and improve the condition of the acid grassland on the north side of Ossetts Hole Lane and to the east of the track to East View and Dovecote and undertake the long-term annual management of acid grassland.
18 | Biodiversity A/C | HOW: Remove holly etc. Achieved by scrub removal, especially the dense patches of holly, and the removal of younger trees, pushing back the edges of the woodland to open up the area. Outside bird nesting season. | Estimate | 1 | Item | Sept to Jan | 2400 | 2400 |  | In his budget David Cole allowed £2,400 for 3 years, Total £7,200 in 2019, 2020 & 2021,started in 2023, but more to do, not all money spent.
19 | Biodiversity A/C | HOW: Scrape leaf litter and fertile topsoil (2-5cm)and scrape into habitat piles. | Estimate | 1 | Item | Check re GCNs. | 600 | 600 |  | In his budget David Cole allowed £600 for 3 years, Total £1,800 in 2019, 2020 & 2021, not started, money not spent.
20 | Operating A/C | Long Term Annual Management of Acid Grassland:
21 | Operating A/C | HOW: Cut grassland and remove cuttings, composting cuttings on site. | [7 empty] | In his budget David Cole allowed £150 per year starting in 2022, not started, money not spent.
22 | Biodiversity A/C | PONDS:
23 | Biodiversity A/C | Enhance Pond 1, near Dinglebury:
24 | Biodiversity A/C | How: Remove fallen trees. | Xtreme Tree Care |  |  | Completed Sept 2023 |  | 0 |  | XTREME invoice £1,350 + VAT.
25 | Biodiversity A/C | How: Plant common reed. £3,500 - £1,350 = £2,150 left to spend. | Estimate | 1 | Item |  | 2150 | 2150 |  | In his budget David Cole allowed £3,500 in 2019, fallen trees removed, so started but more to do, not all money spent.
26 | Biodiversity A/C | Enhance Pond 2, near East View and Dovecote:
27 | Biodiversity A/C | HOW: By attempting to improve water quality and pond habitat quality for great crested newts by scrub removal, especially the dense patches of holly, and the removal of younger trees, pushing back the edges of the woodland thus increasing light levels to the pond. | Included in Row 19 above, Remove holly etc. |  |  |  |  | 0 |  | By Item / Row 18 above. HOW: Remove holly etc. Achieved by scrub removal, especially the dense patches of holly, and the removal of younger trees, pushing back the edges of the woodland to open up the area.
28 | Biodiversity A/C | Enhance Pond 6, near Olga:
29 | Biodiversity A/C | HOW: Remove scrub, treat any stumps and remove cuttings. | Completed. |  |  | Completed. |  | 0 |  | In his budget David Cole allowed £2,600 in 2019, is money all money spent?
30 | Biodiversity A/C | HOW: Desilt & excavate pond. | Completed. |  |  | Completed. |  | 0 |  | In his budget David Cole allowed £2,400 in 2019, is money all money spent?
31 | Biodiversity A/C | Miscellaneous
32 | Biodiversity A/C | Hire Stump Grinder. | HireBase. SKU:0929. | 3 | W/E | As required. | 142.05 | 426.15 |  | Outside bird nesting season.
33 | Biodiversity A/C | Hire Chipper Grinder. Towable, price on application. | HireBase. Estimate | 4 | W/E | As required. | 250 | 1000 |  | Outside bird nesting season.
34 | Biodiversity A/C | Wild Bee Boxes. Possibly make / buy some wild bee boxes. | Amazon | 10 | Item | As required. | 10.99 | 109.9 |  | https://www.amazon.co.uk/Garden-Wooden-Nesting-Natural-Shelter
35 | Biodiversity A/C | Hedgehog Boxes. Possibly make / buy some hedgehog boxes. | Amazon | 10 | Item | As required. | 39.99 | 399.9 |  | SCOBUTY 7188042 Wooden Hedgehog House, Solid Wood Garden Sanctuary, Wildlife Hibernation Shelter, Brown : Amazon.co.uk: Garden
36 | Biodiversity A/C | David Cole - Ecological Monitoring. |  | 1 | Item |  |  | 0 |  | Not until 2028-29
37 | Biodiversity A/C | David Cole - Contract Renewal. |  | 1 | Item |  | 500 | 500
38 | Biodiversity A/C | David Cole - Contract Monitoring. |  | 1 | Item |  | 150 | 150
39 | Biodiversity A/C | David Cole - Ecological Advice. |  | 1 | Item |  |  | 0 |  | Not until 2027-28
40 | Biodiversity A/C | David Cole - Management Plan Review. |  | 1 | Item |  |  | 0 |  | Not until 2033-34